## Gantt
| Predicted Time Needed (Hours) | Time Spent (Hours) | Key |  | Completed |  |  | This Week |  |  | Planned
Yiqing Team Lead 6 |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Requirements Collection | 5 | 3 | bar: 3
Character control(movement,camera,block and obstacle)) design | 6 | 6 | bar: Completed 6 to Completed 9
Design and Programming Camera following character | 6 | 4 | bar: Completed 12 to This Week 15
Programming movement | 18 | 10 | bar: This Week 15 to Planned 36
Programming hit obstacle and animation | 15 | 6 | bar: This Week 15 to Planned 45
Testing individual and debug | 10 | 3 | bar: Planned 45 to Planned 51
User Documentation | 6 | 3 | bar: Planned 54 to Planned 60
Installation | 2 | 0
Total: | 68 | 35