## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit/Excess | Budgeted | Actual | Deficit/Excess | Budgeted | Actual | Deficit/Excess | Budgeted | Actual | Deficit/Excess
Jaidin | 2550 | 1450 | 1100 | 1150 | 1200 | -50 | 1000 | 250 | 750 | 400 | 0 | 400
Aaron | 5100 | 1200 | 3900 | 3700 | 0 | 3700 | 1000 | 400 | 600 | 400 | 800 | -400
Lenin | 1500 | 450 | 1050 | 200 | 100 | 100 | 1000 | 250 | 750 | 300 | 100 | 200
Jeff | 7100 | 400 | 6700 | 5500 | 0 | 5500 | 1000 | 400 | 600 | 600 | 0 | 600
Irven | 6700 | 800 | 5900 | 5400 | 400 | 5000 | 1000 | 400 | 600 | 300 | 0 | 300
Yiqing | 5500 | 700 | 4800 | 4200 | 300 | 3900 | 1000 | 400 | 600 | 300 | 0 | 300
Total | 28450 | 5000 | 23450 | 20150 | 2000 | 18150 | 6000 | 2100 | 3900 | 2300 | 900 | 1400

## Gantt
| Predicted Time Needed (Hours) | Time Spent (Hours) | Key |  | Completed |  |  | This Week |  |  | Planned
Jaidin Team Lead 1 |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
Initial Unity Setup | 1.5 | 1
Initial Code Repo Setup | 2 | 2
Champion | 2 | 2 | bar: 3
Request For Proposal | 2.5 | 2.5 | bar: Completed 6
Sequenc e + Class Diagrams | 1.5 | 2.5
Team Lead Presentation | 2 | 2
Total: | 11.5 | 12
Aaron Team Lead 2
Requirements Collection | 2 | 0
Track Design | 3 | 0 | bar: 3
Character Design | 3 | 0 | bar: Completed 6
Background Design | 3 | 0 | bar: Completed 9
View Track Functionality | 4 | 0 | bar: Completed 12 to This Week 15
View Background Functionality | 4 | 0 | bar: This Week 18 to This Week 21
View Character Functionality | 4 | 0 | bar: Planned 24 to Planned 27
View Obstacles Functionality | 6 | 0 | bar: Planned 30 to Planned 33
Create Testing Functionality | 4 | 0 | bar: Planned 36 to Planned 39
Integrate With Other Components | 4 | 0 | bar: Planned 42 to Planned 45
Total: | 37 | 0
Lenin Team Lead 3
Obstacle Images | 2 | 1
Obstacle Purpose/Interactions
Coin Generation
Total: | 2 | 1
Jeff Team Lead 4
HUD Layout | 5 | 0 | bar: 3
Score Control | 10 | 0 | bar: Completed 6 to Completed 12
Display Score | 10 | 0 | bar: This Week 15 to Planned 24
Implmentation of Mulitplier & Display | 10 | 0 | bar: Planned 27 to Planned 33
Song Score Implementation & Time Display | 10 | 0 | bar: Planned 36 to Planned 42
Menu Button Implementation and Display | 10 | 0 | bar: Planned 45 to Planned 54
Total: | 55 | 0
Irven Team lead 5
Main Menu | 10 | 2 | bar: 3 to Completed 9
Help Menu | 3 | 0 | bar: Completed 12
Track Selection | 5 | 0 | bar: This Week 15 to This Week 18
Play Button | 5 | 1 | bar: This Week 21 to Planned 24
Exit Button | 1 | 1 | bar: Planned 27
Sound Controls | 20 | 0 | bar: Planned 30 to Planned 48
Hotkey Assignment (Bindings) | 5 | 0 | bar: Planned 51 to Planned 54
| 5 | 0 | bar: Planned 57 to Planned 60
Total: | 54 | 4
Yiqing Team Lead 6
1. Requirements Collection | 5 | 3 | bar: 3
2. Character control(movement) design | 6 | bar: Completed 6 to Completed 9
3. Character control(block and obscale) design | 6 | bar: Completed 12 to This Week 15
4. Programming | 9 | bar: This Week 18 to Planned 24
5. Testing individual | 5 | bar: Planned 27 to Planned 30
6. User Documentation | 5 | bar: Planned 33 to Planned 36
7. Combine coding testing | 4 | bar: Planned 39
8. Installation | 2 | bar: Planned 42
Total: | 42 | 3
Group Totals (Hours) | 201.5 | 20
Group Totals ($) | 20150 | 2000
Difference (Hours) | 181.5
Difference ($) | 18150

## Meetings
| Date | Jan. 24 | Jan. 30 | 2019-02-05 | 2019-02-06 | TBD | TBD | TBD | TBD | TBD | TBD
| Purpose | First Meeting | Discuss Features | Champ/Pres. | Champ/Pres.
| Hours | 1 | 1.5 | 1 | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
Jaidin | 2.5 | ü | x | ü | ü
Aaron | 4 | ü | ü | ü | ü
Lenin | 2.5 | ü | x | ü | ü
Jeff | 4 | ü | ü | ü | ü
Irven | 4 | ü | ü | ü | ü
Yiqing | 4 | ü | ü | ü | ü
Total | 21 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Key: | Present | ü | Away | x
Key:

## SA
| Task | Predicted(Hours) | Spent(Hours) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Jaidin | Champion | 2 | 0 | bar: 1 to 2; 15
| RFP - 3 | 1 | 0 | bar: 3; 15
| Presentation | 1 | 0 | bar: 4 to 5; 15
| Subtotal | 4 | 0
Aaron | Champion | 2 | 4 | bar: 1 to 5; 15
| RFP - 1 & 2 | 1 | 2 | bar: 5 to 6; 15
| Presentation | 1 | 2 | bar: 7 to 8; 15
| Subtotal | 4 | 8
Lennin | Champion | 1 | 0 | bar: 1; 15
| RFP - 6 & 8 | 1 | 0 | bar: 2; 15
| Presentation | 1 | 0 | bar: 3; 15
| Subtotal | 3 | 0
Jeff | Champion | 2 | 6 | bar: 1 to 6; 15
| RFP - 7 | 2 | 1 | bar: 7; 15
| Presentation | 2 | 1 | bar: 8; 15
| Subtotal | 6 | 8
Irven | Champion | 1 | 0 | bar: 1; 15
| RFP - 3 | 1 | 0 | bar: 2; 15
| Presentation | 1 | 0 | bar: 3; 15
| Subtotal | 3 | 0
Yiquing | Champion | 1 | 0 | bar: 1; 15
| RFP - 4 & 5 | 1 | 0 | bar: 2; 15
| Presentation | 1 | 0 | bar: 3; 15
| Subtotal | 3 | 0
| Total | 23 | 16
Key
Dependent On Others
Total
Subtotal
Time Slots