## Gantt
| Predicted Time Needed (Hours) | Time Spent (Hours) | Key |  | Completed |  |  | This Week |  |  | Planned
Yiqing Team Lead 6 |  |  | Hours | 3 | 6 | 9 | 12 | 15 | 18 | 21 | 24 | 27 | 30 | 33 | 36 | 39 | 42 | 45 | 48 | 51 | 54 | 57 | 60 | 63 | 66 | 69 | 72 | 75 | 78
1. Requirements Collection | 5 | 3 | bar: 3
2. Character control(movement) design | 6 | bar: Completed 6 to Completed 9
3. Character control(block and obscale) design | 6 | bar: Completed 12 to This Week 15
4. Programming | 9 | bar: This Week 15 to Planned 24
5. Testing individual | 5 | bar: Planned 27 to Planned 30
6. User Documentation | 5 | bar: Planned 30 to Planned 36
7. Combine coding testing | 4 | bar: Planned 39
8. Installation | 2 | bar: Planned 42
Total: | 42 | 3